Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 10 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS26598 |
| Project Name | Prevent User Deletion If Assigned to Incident |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Requirement Analysis | USN-1 | As an admin, I want to analyze the issue of accidental user deletion in ServiceNow. | 2 | High | Likitha |
| Sprint-1 | Table Study | USN-2 | As a developer, I want to understand the relationship between sys_user and incident tables. | 2 | High | Jyoshna |
| Sprint-1 | Design Planning | USN-3 | As a team, we want to design logic flow for deletion validation. | 3 | High | Akash |
| Sprint-2 | Business Rule Creation | USN-4 | As a developer,I want to create a Before Delete Business Rule on sys_user table. | 4 | High | Gnanendra |
| Sprint-2 | GlideRecord Logic | USN-5 | As a developer, I want to query the incident table to check assigned incidents. | 4 | High | Likitha |
| Sprint-2 | Error Handling | USN-6 | As a system admin, I want to display an error message when deletion is blocked. | 2 | Medium | Jyoshna |
| Sprint-3 | Testing | USN-7 | As a tester, I want to verify deletion blocking when incidents exist. | 3 | High | Akash |
| Sprint-3 | Validation | USN-8 | As a tester, I want to ensure deletion works for unassigned users. | 2 | Medium | Gnanendra |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 8 | 6 Days | 4 January 2026 | 9 January 2026 | 8 | 9 January 2026 |
| Sprint-2 | 10 | 6 Days | 19 January 2026 | 24 January 2026 | - | - |
| Sprint-3 | 8 | 6 Days | 26 January 2026 | 1 February 2026 | - | - |
| Sprint-4 | 7 | 6 Days | 14 February 2026 | 19 February 2026 | - | - |

Velocity:

Assume:

- Sprint Duration = 6 Days

- Total Story Points in Sprint-1 = 8

Average Velocity (AV) per day:

AV = Total Story Points / Sprint Duration

AV = 8 / 6 = 1.33 Story Points per Day

If team capacity improves, expected velocity per sprint ≈ 8–10 points per sprint

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts